## Sheet1
Milestone | Task | Start Date | End Date | Duration | Responsible Group Member
Commence Project |  | 2020-03-31 | 2020-03-31 | 0 | All
| Development of Idea | 2020-03-31 | 2020-04-10 | 10
| Data Collection | 2020-04-02 | 2020-04-09 | 7 | Luca
| Data Cleaning and Reduction | 2020-04-02 | 2020-04-09 | 7 | Luca
| Initial Data Explanations | 2020-04-07 | 2020-04-16 | 9 | Bethany
| Initial Data Analysis | 2020-04-07 | 2020-04-16 | 9 | Luca and Jakob
| Visualisation Planning | 2020-04-10 | 2020-04-16 | 6 | Bethany
| Creation of Video | 2020-04-16 | 2020-04-20 | 4 | Bethany
PA A Submission |  | 2020-03-31 | 2020-04-20 | 20
PA A Peer Evaluations |  | 2020-03-31 | 2020-04-27 | 27
| Data Manipulation | 2020-04-21 | 2020-04-28 | 7 | Jakob
| Initial Creation of Visualisations | 2020-04-21 | 2020-04-28 | 7 | Group
| Editing of Visualisations | 2020-04-28 | 2020-05-05 | 7 | Luca
| Refinement of Visualisations | 2020-04-28 | 2020-05-05 | 7 | Bethany
| Creation of Website | 2020-04-28 | 2020-05-05 | 7 | Jakob
| Presentation of Visualisations | 2020-05-05 | 2020-05-11 | 6 | Bethany
| Explanations and Discussions | 2020-05-05 | 2020-05-13 | 8 | Group
| Final Editing | 2020-05-11 | 2020-05-15 | 4 | Bethany
PA B Submission |  | 2020-03-31 | 2020-05-15 | 45
PAB Peer Evaluations |  | 2020-03-31 | 2020-05-22 | 52